# 03 — Multi-Tenant Accounts (XL — Biggest Feature)

Revision: 1 Parent: 00_MASTER_INDEX.md Prerequisites: A-01, A-02 (Accounts design decisions) MUST be resolved first. Source: docs/research/accounts/30_delivery_plan.md (8 milestones, Rev 1, 2026-07-10)

## Overview

The Accounts feature adds a TENANT (account) layer above the current Project layer. Every resource (device, artifact, release, deployment, telemetry) becomes scoped to an Account. This is the single largest feature remaining — estimated XL effort across 8 milestones.

Critical path: M1 → M2 → M3 → (M7 object-storage seam) → M4/M5/M6 e2e → M8 retest+merge.

Work-stream setup (§11.4.167): Develop on branch feature/multi-tenant-accounts in an isolated reflink/CoW copy with its own .git. Merge main in regularly (§11.4.188). NEVER force-push.

## C-01 [AGENT] — M1: Data Model + Migrations + Store Scoping (XL)

Source: accounts/30_delivery_plan.md §2 M1

### What to build:

- New entities in store/store.go:

  - Account (account_id, name, slug, status active/suspended/archived, timestamps)

  - User (user_id, username, password_hash — replaces the in-memory UserDirectory)

  - Membership (user_id, account_id, role, is_owner)

- Migration 11 (or 3 in the Accounts plan numbering):

  - Add account_id TEXT NOT NULL DEFAULT '' to: devices, artifacts, releases, deployments, telemetry_events, device_groups, audit_logs, delta_artifacts, rollback_history, rollout_states, rollout_phases, branches, webhooks, delta_metadata.

  - Add per-table composite UNIQUE keys including account_id.

  - Backfill existing rows: UPDATE <table> SET account_id = '__default__' WHERE account_id = ''.

  - Create the __default__ account.

- Store interface extension:

  - CreateAccount, GetAccount, ListAccounts, UpdateAccount, ArchiveAccount, SuspendAccount

  - CreateUser, GetUser, GetUserByUsername

  - AddMembership, RemoveMembership, ListMemberships

  - Account-scoped variants of ALL existing methods (e.g., ListDevicesByAccount)

- Implement in BOTH backends:

  - MemoryRepository — full account isolation (in-memory maps keyed by account_id)

  - PostgresRepository — RLS policies per-account (migration with ALTER TABLE ... ENABLE ROW LEVEL SECURITY)

- Tests: TestAccountCRUD_Memory, TestAccountCRUD_Postgres, TestAccountIsolation_Memory, TestAccountIsolation_Postgres, TestMigration11_Backfill, TestDevicesScopedToAccount

## C-02 [AGENT] — M2: Token account_id Claim + Super-Admin AuthZ + Role Vocabulary (L)

Source: accounts/30_delivery_plan.md §2 M2

### What to build:

- Token extension: Add account_id claim to access/refresh tokens (server/internal/api/token.go).

- Token verification: authMiddleware extracts account_id from token, sets on context.

- Super-admin role: A super_admin role that bypasses account scoping (sees ALL accounts’ data).

- Role vocabulary SSOT: Single canonical enum for all roles across server + both SPAs.

- AuthZ middleware: requireAccountAccess — gate routes by token’s account_id.

- Tests: TestTokenCarriesAccountId, TestSuperAdminBypassesAccountScope, TestNonAdminCannotCrossAccount

## C-03 [AGENT] — M3: Account-Scope Every OTA Route + Super-Admin API + List Artifacts (L)

Source: accounts/30_delivery_plan.md §2 M3

### What to build:

- Account-scope every existing route:

  - /api/v1/accounts/:accountId/projects — list projects in account

  - /api/v1/accounts/:accountId/updates — list available updates

  - /api/v1/accounts/:accountId/devices — register device for account

  - Device registration must bind to the token’s account_id

- Super-admin API (/api/v1/admin/*):

  - GET/POST /admin/accounts — list/create accounts

  - GET/PATCH/DELETE /admin/accounts/:id — manage accounts

  - POST /admin/accounts/:id/suspend — suspend account

  - POST /admin/accounts/:id/unsuspend — unsuspend account

  - POST /admin/accounts/:id/members — set account membership

- Missing endpoint: GET /artifacts (list artifacts — gap tracker G-07 mentions this was missing).

- Backward compatibility: Unscoped routes continue to work for __default__ account.

- Tests: TestAccountScopedRoutes, TestSuperAdminAPIFullCRUD, TestCrossAccountRejected

## C-04 [AGENT] — M4: UI — Sign-In Split + Account Switcher + Super-Admin Console (L)

Source: accounts/30_delivery_plan.md §2 M4

### What to build:

- Dashboard (dashboard/):

  - Post-login account picker (if user has multiple memberships)

  - Account switcher in header (above project switcher)

  - Super-admin console: account CRUD, member management, suspend/unsuspend

- ota-manager (clients/ota-manager/):

  - Same: account picker post-login

  - Account switcher in sidebar

  - Super-admin console with same capabilities

- Host-render proof (§11.4.170): Every new screen, light+dark, golden image-diff + OCR layout oracle.

- Tests: Playwright/axe a11y, host-render visual regression.

## C-05 [AGENT] — M5: Project-Side Integration CLI (M)

Source: accounts/30_delivery_plan.md §2 M5

### What to build:

- New binary: server/cmd/helix-ota/main.go — CLI for CI/CD pipelines.

- Commands:

  - helix-ota login --server <url> --username <u> --password <p> → token

  - helix-ota select-account <account-slug> → account-scoped token

  - helix-ota upload <artifact.zip> --project <id> → upload artifact to project

  - helix-ota create-release --artifact <id> --version <v> → create release

  - helix-ota create-deployment --release <id> --group <name> → create deployment

- Auth: Reads token from ~/.config/helix-ota/auth.json, refreshes automatically.

- Tests: TestCLILoginFlow, TestCLIUploadArtifact, TestCLIFullWorkflow

## C-06 [AGENT] — M6: Device Update Client + Setup Wizard (XL)

Source: accounts/30_delivery_plan.md §2 M6

### What to build:

- ota-android-agent:

  - Multi-account production client: device registers to a specific account via setup wizard

  - Server-minted device identity (device token bound to account)

  - Per-account signature verification (public key registry per account)

  - Setup/notification/consent wizard UI

- Device registration flow:

  - Wizard shows QR code or pairing code

  - Operator scans/enters on dashboard to approve

  - Device receives token, polls for updates scoped to its account

- Dependency on M7: The byte-level “downloads + applies exact bytes” e2e proof is gated on the object-storage seam landing (M7). M6’s control-plane work lands on schedule; the device-side e2e is SKIP-with-reason: object_storage_absent until M7.

- Tests: TestDeviceRegistersToAccount, TestDeviceOnlySeesOwnAccountUpdates, TestPerAccountSignatureVerify

## C-07 [AGENT] — M7: Object Storage Seam + Security Hardening (L)

Source: accounts/30_delivery_plan.md §2 M7

### What to build:

- Real StoragePort implementation:

  - s3_storage.go already EXISTS (server/internal/store/s3_storage.go, 188 lines).

  - StorageRef is already a type. Verify it actually stores bytes (not just validates-then-discards).

  - If placeholder: implement Put(ctx, artifactId, reader, size) → StorageRef using MinIO client.

  - Implement Get(ctx, ref) → io.ReadCloser for download.

  - Implement SignedURL(ctx, ref, expiry) → string for temporary download URLs.

- Per-account signing-key registry:

  - Table: signing_keys (account_id, key_id, public_key, created_at, expires_at, active)

  - Routes: POST /admin/accounts/:id/keys, GET /accounts/:accountId/keys

  - Key rotation: support HELIX_ARTIFACT_PREVIOUS_PUBKEY per-account.

- Secret fail-fast (per-account):

  - Each account MUST have at least one active signing key before artifacts can be uploaded.

- Tests: TestS3StoreRoundTrip, TestSignedURLExpires, TestPerAccountKeyRotation

## C-08 [AGENT] — M8: Full Retest + Manual QA Merge Gate (M)

Source: accounts/30_delivery_plan.md §2 M8

### What to do:

- Full test sweep from clean baseline:

  - cd server && go test -race -count=1 ./... → ALL GREEN

  - cd submodules/ota-protocol && go test -race ./... → GREEN

  - cd submodules/ota-rollout-engine && go test -race ./... → GREEN

  - cd submodules/ota-artifact-validator && go test -race ./... → GREEN

  - cd submodules/ota-telemetry-schema && go test -race ./... → GREEN

  - PostgreSQL integration tests: POSTGRES_TEST=1 go test -tags integration ./server/internal/store/...

  - Kotlin tests: ./gradlew test in ota-android-agent, ota-update-engine-bridge

  - Dashboard: pnpm test:run + Playwright e2e + host-render

  - ota-manager: pnpm test:run + vitest

- Independent code review (§11.4.125/§11.4.134): Independent verifier reviews ALL new code, iterates to zero-finding GO.

- [OPERATOR] §11.4.185 Manual QA final confirmation on:

  - Multi-account creation and isolation

  - Cross-account access rejection

  - Per-account artifact upload and signing

  - Device registration to specific account

  - OTA update cycle within a single account

  - Super-admin operations across accounts

- Operator approval → merge feature/multi-tenant-accounts → main (§11.4.167).

## Dependency Chain (Critical Path)

A-01/A-02 resolved
    │
    ▼
C-01 M1 (XL) ──────► C-02 M2 (L) ──────► C-03 M3 (L)
    │                                           │
    │                              ┌────────────┘
    │                              ▼
    │                         C-07 M7 (L) ── object storage seam
    │                              │
    │              ┌───────────────┼───────────────┐
    │              ▼               ▼               ▼
    │         C-04 M4 (L)    C-05 M5 (M)    C-06 M6 (XL)
    │              │               │               │
    └──────────────┴───────────────┴───────────────┘
                                                   │
                                                   ▼
                                              C-08 M8 (M)
                                              retest + QA + merge

## Honest Boundary (§11.4.6)

- The Accounts design (docs 00_INDEX.md through 30_delivery_plan.md) is thorough and complete. Zero production code exists for any M1-M8 milestone.

- M1 alone is XL effort — it touches the data model of EVERY table in both store backends.

- The object-storage seam (M7) already has scaffolding (s3_storage.go) but may still be a placeholder that discards bytes after validation. Verify before relying on it.

- This is the LONGEST pole in the production-readiness tent. All other stages (except G — System Images) can complete while Accounts is in progress.

- The Accounts feature branch should merge main in regularly (§11.4.188) to avoid a massive conflict-resolution at the end.